## Sheet1
Start Date | Task | Estimated Hours
2022-07-01 | Make a Project Plan | 0.5
2022-07-01 | Make a Trello Board | 0.5
2022-07-01 | Set Up Azure Cloud Shell & clone new repo | 1
2022-07-01 | Configure GitHub Actions | 1
2022-07-01 | Set Up Azure DevOps | 0.5
2022-07-01 | Integrate new Repo with Pipelines | 0.5
2022-07-01 | Manually Deploy Starter Code to Web App & test | 1
2022-07-02 | Create Azure Service Connection | 0.5
2022-07-02 | Set Up Agent Pool & Linux VM Agent | 1
2022-07-02 | Create a Pipeline | 1
2022-07-02 | Documentation | 1.5