## Sheet1
Start Date | Task | Estimated Hours
2022-07-01 | Make a Project Plan | 0.5
2022-07-01 | Make a Trello Board | 0.5
2022-07-01 | Set Up Azure Cloud Shell & clone new repo | 1
2022-07-01 | Configure GitHub Actions | 1
2022-07-01 | Set Up Azure DevOps | 0.5
2022-07-01 | Integrate new Repo with Pipelines | 0.5
2022-07-01 | Manually Deploy Starter Code to Web App & test | 1
2022-07-02 | Create Azure Service Connection | 0.5
2022-07-02 | Set Up Agent Pool & Linux VM Agent | 1
2022-07-02 | Create a Pipeline | 1
2022-07-02 | Documentation | 1.5
Quaterly Plan | Features | Proposed Difficulty | Feature Category | Status
Q1 | Prepare for Project resources & team allocation | 3 | Project Initialization | Done
Q2 | Design a Model to give predictions, and link it to API | 1 | MVP | Done
Q3 | Implement CI CD for the project | 2 | CI/CD | In Progress
Q4 | Improve Quality Assurance | 2 | QA | To Do